## Sheet1
Category | Risk Description | Likelihood | Impact | Risk Score | Mitigation Strategy | Owner | Target Completion
PR.IP-12 | Cross-Domain Solution (CDS) controls incomplete, increasing potential for unauthorized data transfer between classified and unclassified domains. | High | High | 9 | Implement remaining STIG requirements; perform Red/Blue team validation. | H. Simpson | 2025-09-30
ID.RA-1 | Critical unpatched CVE in fleet management application could allow remote code execution impacting operational readiness. | Medium | High | 8 | Patch deployment in staging followed by full security regression testing. | M. Simpson | 2025-08-25
PR.MA-1 | Lack of documented quarterly ACAS vulnerability scans in eMASS reduces RMF compliance evidence. | Medium | Medium | 6 | Complete ACAS scans and upload to eMASS with signed ISSM approval. | L. Simpson | 2025-08-15
PR.AT-1 | Delayed completion of annual cyber awareness training increases insider threat risk. | Low | Medium | 4 | Conduct training and track completion in LMS with Navy COR oversight. | B. Simpson | 2025-08-20