## Sheet1
Priority | NIST CSF Category | Risk | Fix Action | Finding Date | Target Date | POC | Status | Open/Closed
1 | PR.IP-12 | Cross-Domain Solution (CDS) security controls not fully implemented per RMF Step 4 assessment | Implement and validate all STIG and NSA-approved CDS controls; perform end-to-end functional and security testing. | 2025-07-15 | 2025-09-30 | H. Simpson | Engineering review in progress; CDS STIG checklist at 80% completion | Open
2 | ID.RA-1 | Unpatched CVE-2025-4321 in fleet management application (critical RCE vulnerability) | Apply vendor patch, conduct regression testing in staging, and push to production with Navy cybersecurity approval. | 2025-08-01 | 2025-08-25 | M. Simpson | Vendor patch received; awaiting change control board review | Open
3 | PR.MA-1 | Quarterly vulnerability scans not documented in eMASS for OSG enclave | Perform ACAS scans, upload results to eMASS, and maintain POA&M closure evidence. | 2025-06-10 | 2025-08-15 | L. Simpson | ACAS scan completed; results under ISSM review | Open
4 | PR.AT-1 | Annual cyber awareness training for Navy contractor staff not yet completed | Schedule and conduct training for all OSG enclave privileged and non-privileged users. | 2025-05-20 | 2025-08-20 | B. Simpson | Training scheduled; materials under review by ISSO | Open